## Overview
andSons CRM Demo — Project Tracker
Last updated: 05 August 2026
Two pipelines: AI email generation (Copywriter -> Sweeper -> Feedback loop) and natural-language analytics chat, plus Slack + hosting.
Pipeline / Track | Status | What's live | Biggest open item
Email Generation | Done | Copywriter + Sweeper + Feedback loop; bank-only hero images (18 real photos); brand-voice QA guardrails. | None - fully working and deployed.
Analytics Chat | Done | LangChain SQL agent over live andSons BigQuery data (with mock-data fallback); write + PII guardrails. | BigQuery service account has broader (Editor) access than needed - ask to narrow it.
Slack Integration | Blocked | /andsons-email and /andsons-ask slash commands built and tested end-to-end. | Needs a Slack app created in the office workspace (requires workspace admin).
Hosting (Render) | Done | Live at andsons-crm-demo.onrender.com, auto-deploys on push to main. | Free tier: no persistent disk (mock DB resets on redeploy), cold starts after 15 min idle.
GitHub Repo | Done | Private repo harikrishna-ora/andsons-crm-demo, connected to Render for auto-deploy. | None.
Status legend
Done
In Progress
Blocked
Pending
See the other tabs for a full task-level breakdown of each pipeline.

## Email Generation
Email Generation Pipeline
Component | Status | Description | Notes
Copywriter agent | Done | Drafts structured email JSON (subject, preheader, body, CTA, optional blocks) in the real andSons brand voice. | Grounded in real flow briefs (backend/flows.py) and the approved P1 golden template.
11 lifecycle flows | Done | P1 Plan Not Purchased, P2 Consult No-Show, P3 OTC Cart Abandon, The Valley, Consult Booking, Replenishment/Dunning, Rx-Not-Suitable-to-OTC, AOV Growth, Winback, Results Milestone, Quiz Recovery. | Each flow has its own track (rx/otc/neutral), audience, goal, and price rule.
Brand voice & compliance rules | Done | British spelling, no em-dashes, no exclamation marks, CTA = verb + My + noun, no Rx medicine names, doctor attribution, DOI-footnoted stats only, no cure/guarantee language. | Sourced from the real andSons CRM knowledge base, not invented.
Sweeper agent (brand QA gate) | Done | LLM + deterministic checks against the 8-point compliance checklist before an email is shown. | Two-layer: Python ground-truth checks plus an LLM judgement pass.
Feedback loop (auto-retry) | Done | On a Sweeper fail, re-runs the Copywriter with the full original prompt plus the specific correction, up to 2 retries. | Falls back to needs_human_review instead of looping forever.
Human feedback revision | Done | A reviewer can type free-text feedback and regenerate; keeps full draft + feedback history so a new note can't undo an earlier one.
Hero image bank | Done | 18 real approved photos curated directly from the Image_Bank asset folder, including real alternate P1 hero exports and product shots. | Selection is bank-only, per manager decision - no AI image generation.
Hero image generation (OpenAI) | Removed | Originally built as a fallback for when no bank photo fit; removed on manager instruction to use bank-only selection. | image_gen.py deleted; all OPENAI_* config removed.
Hero images served locally | Done | Bank photos re-encoded and served directly by Flask at /hero-images/<key>.jpg - no external host needed. | Works identically locally and on Render.
Hero selection quality | Done | Fixed a bug where the model only ever saw bare image keys (no descriptions), causing it to repeatedly default to 1-2 'safe-sounding' images. | Now sees the full photo catalog with descriptions - much better variety.
Copy quality / natural language | Done | Fixed generic, brochure-style phrasing (e.g. "Your private consult") in hero headlines and email copy; banned clinical filler words. | Headlines now read like something a person would actually say.
Frontend rendering | Done | Hero image + overlay headline rendered at the top of the email card; Sweeper pass/fail history and feedback box in the UI.
Slack slash command (/andsons-email) | Done | Runs the full pipeline and posts the drafted email (incl. hero image) to the Slack channel. | Needs the Slack app created before it can be used - see Slack Integration tab.

## Analytics Chat
Analytics Chat Pipeline
Component | Status | Description | Notes
LangChain SQL agent | Done | Answers natural-language questions by writing and running real SQL against the active database. | Model writes SQL directly against the introspected schema.
Mock SQLite database | Done | Synthetic customers/campaigns/orders/marketing-spend data, grounded in real BigQuery column names and semantics. | Used automatically whenever live BigQuery isn't configured or reachable.
Number-grounding verification | Done | Every number in the final answer is checked against the actual query result; unverifiable answers are replaced with an explicit refusal. | Includes a derivability check for percentages/rates computed in prose.
Write-query guardrail | Done | Blocks any INSERT/UPDATE/DELETE/DROP-style request, both in the user's question and in any SQL the agent tries. | Backed by a read-only DB connection for the mock database.
Customer PII guardrail | Done | Refuses to state an individual customer's email or personal details; aggregates only. | Enforced at the prompt level and independently double-checked in code.
Live BigQuery connection | Done | Connects to the real ORA data warehouse (ora_bigquery_pipeline) with automatic fallback to mock data if unreachable. | Confirmed real andSons rows via Brand = 'AndSons' filtering.
Correct dataset identification | Done | Traced down the real andSons data after discovering the first connected dataset was actually a different ORA brand (Ova). | Verified via real product-catalog inspection, not assumed.
Table allowlist (BIGQUERY_TABLES) | Done | Restricts the agent to the 3 real tables that matter (dotcom_plus_marketplace, updated_sales_data, marketing_spend_data). | Prevents wandering into another brand's replica or a stale snapshot table.
Brand/country filtering discipline | Done | System prompt hard-codes Brand='AndSons' AND Country='Singapore' as the default filter, since the real tables mix every brand/country together.
Graceful "no data" fallback | Done | Questions the data genuinely can't answer (e.g. email open/click tracking, which doesn't exist in either database) now get a clear explanation instead of looping. | Previously surfaced as "Agent stopped due to max iterations".
Answer quality / no DB jargon | Done | Rewrote answer-style instructions so responses lead with the number, add one real breakdown, and never leak words like "row", "table", "Category-Level". | Reads as analyst commentary, not a query description.
Slack slash command (/andsons-ask) | Done | Runs the question through the analytics agent and posts the answer, SQL, and verification/source status to Slack. | Needs the Slack app created before it can be used - see Slack Integration tab.
BigQuery service account scope | In Progress | The provisioned service account (hari-ora-service-account) currently has project-wide Editor access. | Ask whoever administers ora-bigquery to narrow it to BigQuery Data Viewer + Job User only.

## Infrastructure & Deployment
Infrastructure & Deployment
Item | Status | Description | Notes
GitHub repository | Done | Private repo harikrishna-ora/andsons-crm-demo, initialised and pushed. | Secrets (.env, service account keys) are gitignored, never committed.
Render web service | Done | Deployed via render.yaml Blueprint, builds from the repo's Dockerfile, auto-deploys on every push to main. | Live at andsons-crm-demo.onrender.com.
Render free-tier limitations | Pending | No persistent disk on the free plan (mock DB resets on redeploy); cold starts (~30-50s) after 15 min idle. | Upgrade to a paid Starter plan if always-on / persistent storage matters.
GCP project (andsons-crm-demo) | Pending | Created and owned by this account; intended as an alternative Cloud Run hosting path. | Blocked on billing being linked - not pursued once Render worked out.
BigQuery service account key | Done | hari-ora-service-account key uploaded to Render as a Secret File (never committed to git). | Confirmed working, connects to real andSons data.
Slack app | Blocked | Slash commands are built and tested (via a mock Slack signature locally); the actual Slack app has not been created yet. | Needs a workspace admin to create the app or approve you creating one.
OpenAI / image generation | Removed | Was wired up for the hero-image generation fallback; fully removed once the manager decided on bank-only selection. | No OpenAI dependency or API key remains in the project.
Attribution / commit history | Done | Co-Authored-By trailers referencing Claude were stripped from all commit messages and force-pushed.

## Open Follow-ups
Open Follow-ups (things only someone else can unblock)
# | Ask | Who | Why it matters
1 | Create a Slack app in the office workspace (or grant permission to create one) with 2 slash commands: /andsons-email and /andsons-ask. | Workspace admin / senior | Slash commands are fully built and tested - this is the only remaining step to use them in Slack.
2 | Narrow hari-ora-service-account's role on ora-bigquery from Editor to BigQuery Data Viewer + BigQuery Job User. | ora-bigquery project admin | The analytics chat only ever needs read access; Editor is broader than necessary for a tool touching real customer data.
3 | Decide whether Render's free tier is acceptable long-term, or upgrade to a paid plan for persistent storage and no cold starts. | You / budget owner | Free tier resets the mock database on every redeploy and has ~30-50s cold starts after idling.